## Burndown
Backlog | 2 | Days | 0 | 1 | 2 | 3 | 4 | 5
In Progress | 1 | Actual Burndown | 35 | 26 | 16 | #N/A | #N/A | #N/A
Done | 2 | Ideal Burndown | 35 | 28 | 21 | 14 | 7 | 0
Feature | Priority | Estimated Hours | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Feature 1 | 1 | 5 | Backlog | 0 | 0 | 0 | 0 | 0
Feature 2 | 2 | 8 | In Progress | 1 | 3 | 0 | 0 | 0
Feature 3 | 3 | 6 | Done | 3 | 3 | 0 | 0 | 0
Feature 4 | 4 | 9 | Done | 5 | 4 | 0 | 0 | 0
Feature 5 | 5 | 5 | Blocked | 0 | 0 | 0 | 0 | 0
Feature 6 | 6 | 2 | Backlog | 0 | 0 | 0 | 0 | 0
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
How to use this sheet: Populate the table with your features, Estimated hours and Status. The priority column is optional and can be used to easily sort your data. The Status drives the Kanban chart: Features can either be in the Backlog, In Progress or Done. The Status does not affect the Burndown chart. Track the actual hours worked by day as you go through your iteration. The Burndown will update automaticaly based on the data in the calulated cells in E2:J4. The chart can be expanded vertically to add more features without any changes to formulae.